## Features
ID | Section | Page/Component | Feature | Description | Type | Priority | Acceptance Criteria | Test Steps (brief) | Status | Target Release | Dependencies / Notes
F-001 | Product Classifications | ProductClassificationsPage / Tree | Deletion preview modal | When deleting a node that has children, show a modal listing affected descendants and require confirmation. | Enhancement | P1 | Deleting a node with children always shows a preview list and requires explicit confirm; cancel leaves tree unchanged; after confirm, node & descendants are removed and persisted. | Create parent→children; click delete on parent; verify modal lists all descendants; click confirm; reload page; tree reflects deletion; localStorage updated. | Shipped | 2025-09-14 | Persists to localStorage key 'productClassificationsTree'.
F-003 | Product Classifications | ProductClassificationsPage / Tree | Animated expand/collapse with AnimatedCollapse | Use measured content height and max-height transition for smooth open/close on child lists. | Enhancement | P1 | Expand/collapse animations are smooth with no content jump; nested levels animate without clipping. | Toggle multiple depths; observe smooth transition; no layout shift in surrounding content. | Shipped | 2025-09-14 | Performance should remain acceptable for typical depths (≤4).
F-005 | Product Classifications | LocalStorage persistence | Persist tree to localStorage | Save and load classification tree from localStorage `productClassificationsTree`. | New | P1 | Reloading page restores the exact last saved tree; create/edit/delete are reflected after reload. | Make changes; reload; verify persistence. | Shipped | 2025-09-14 | Key name must be 'productClassificationsTree'.
F-006 | Common Component | HierarchicalSelect | Portal rendering to document.body | Dropdown panel renders in a portal to body to avoid clipping inside modals/overflow containers. | Enhancement | P1 | Dropdown never gets clipped by parent overflow; z-index stacking shows panel above modals when expected. | Open in modal and outside; verify panel shows fully; scroll container boundaries don't clip. | Shipped | 2025-09-14 | Ensure cleanup on unmount.
F-007 | Common Component | HierarchicalSelect | Horizontal depth columns | Render each depth as fixed-width horizontal columns (default 220px). | Enhancement | P1 | Selecting a level reveals the next column; columns align; horizontal scroll only if more than viewport. | Select 3-level category; verify columns and selection state; adjust window width and check behavior. | Shipped | 2025-09-14 | Expose `colWidth` and `MAX_DEPTH` as props/internal constants.
F-009 | Category Mapping | CategoryMapping Page | Create mapping flow | Select Mall → Internal Category → Mall Category, then create mapping. | New | P1 | Create button enabled only when all selections made; after create, mapping appears in list. | Pick mall+internal+mallCat; click '매핑 생성'; verify list contains new mapping. | Shipped | 2025-09-14 | UI validates required selections.
F-010 | Category Mapping | CategoryMapping Page | Duplicate prevention | Block creating an active mapping with same (internalCategoryId, mallCategoryId, mallId). | New | P1 | Attempt to add an existing active combination shows warning and does not create duplicate. | Create mapping; try same combo again; verify warning and no duplicate row. | Shipped | 2025-09-14 | Check both id and active state.
F-057 | Security | Global | No plaintext secrets in local storage | Do not store sensitive API keys in plaintext (UI shows warning). | Policy | P1 | UI warns when attempting to save secrets in demo; production design requires server-side storage. | Attempt to enter secret; verify warning appears. | Shipped | 2025-09-14 | Back-end policy required.
F-002 | Product Classifications | ProductClassificationsPage / Modal | Contextual modal sizing | Apply max width per action: root add max-w-3xl, child add max-w-2xl, edit max-w-xl; consistent paddings and spacing. | Enhancement | P2 | Each action opens correct sized modal; no overflow; responsive at common breakpoints. | Trigger each modal; resize window widths; confirm sizing and no overflow. | Shipped | 2025-09-14 | Introduce 'modalClass' per context.
F-004 | Product Classifications | ProductClassificationsPage / Tree | Node selection highlight & event propagation guard | Clicking a node highlights selection; action buttons stop event propagation to avoid toggling selection. | Enhancement | P2 | Click on action buttons does not toggle selection; clicking on node area does; highlight visible to user. | Click node area → highlight; click 'edit'/'delete' button → no selection change; verify via UI state. | Shipped | 2025-09-14 | Use e.stopPropagation on action buttons.
F-008 | Common Component | HierarchicalSelect | Anchored panel & viewport clamp | Panel opens under toggle; clamps within viewport to avoid cut-off. | Enhancement | P2 | Panel is positioned beneath toggle; no overflow off-screen; arrow keys and scroll behave correctly. | Open near viewport edges; verify clamping; test scroll within long lists. | Shipped | 2025-09-14 | Positioning util updates on resize/scroll.
F-011 | Category Mapping | CategoryMapping Page | Activate/Deactivate toggle | Per-mapping active status toggle updates state instantly. | New | P2 | Toggling status reflects immediately in UI; state persists in current session/mock store. | Toggle multiple rows; refresh if persistence wired; verify states. | Shipped | 2025-09-14 | Persistence behavior depends on current data store.
F-012 | Category Mapping | CategoryMapping Page | Delete mapping | Delete mapping via confirmation prompt. | New | P2 | Delete asks for confirm; on confirm row disappears; no orphaned references in UI. | Click delete; confirm; verify removal. | Shipped | 2025-09-14 | Use window.confirm in demo.
F-013 | Category Mapping | CategoryMapping Page | Export mappings to Excel | Export current mall’s mappings to XLSX/CSV with fields: internal path, mall path, status, createdAt. | New | P2 | Download file contains only current mall’s mappings; headers and rows are correct. | Filter by mall; click export; open file and check columns. | Shipped | 2025-09-14 | Filename includes mall name/date.
F-016 | Products | ProductList Page | Search by name or code | Free-text search across product name and product code (case-insensitive). | New | P2 | Searching filters rows accurately; empty query restores all. | Type partial name and code; verify results. | Shipped | 2025-09-14
F-017 | Products | ProductList Page | Classification filter via HierarchicalSelect | Filter products by selected internal classification using HierarchicalSelect. | New | P2 | Selecting a 3-level classification shows only products under that path. | Pick 3-level path; verify filtered rows. | Shipped | 2025-09-14 | Depends on HierarchicalSelect.
F-021 | Products | ProductList Page | Row selection & bulk actions | Per-row and select-all checkboxes; bulk export/activate/deactivate/delete. | New | P2 | Selecting rows enables bulk toolbar; actions apply to selected rows only. | Select few rows; trigger each bulk action (where implemented). | Shipped | 2025-09-14 | Destructive actions should use confirm modal (future server-auth).
F-027 | Products | ProductDetail Page | Margin rate calculation | Display margin rate = (price - cost)/price * 100 rounded integer. | New | P2 | Given price and cost, shown margin matches formula rounding. | Test with sample data; verify math. | Shipped | 2025-09-14
F-032 | Orders | OrderList Page | Search & filters | Search by order no./customer/phone; filter by status, payment method, date range, mall. | New | P2 | Combining filters narrows results; search is case-insensitive and partial match. | Apply multiple filters and search; verify results. | Shipped | 2025-09-14
F-034 | Orders | OrderList Page | Status change with UI log | Change order status via dropdown and show internal log entry (UI only). | Enhancement | P2 | Changing status updates visible state and appends a log entry. | Change to '발송 준비' etc.; verify log line appears. | Shipped | 2025-09-14 | Server-side persistence TBD.
F-056 | Accessibility | Global | ARIA and keyboard navigation pass | Ensure primary buttons/inputs have appropriate aria attributes and tab order works. | Enhancement | P2 | All interactive elements reachable via keyboard; labels present. | Tab through pages; screen-reader spot check. | Shipped | 2025-09-14
F-014 | Category Mapping | CategoryMapping Page | UI indicators for mapped items | Show '매핑됨' tag for internal categories already mapped. | Enhancement | P3 | Mapped internal categories visibly tagged; tag updates on create/delete. | Create mapping; verify tag appears; delete mapping; tag removed. | Shipped | 2025-09-14
F-015 | Navigation | Sidebar / Routing | Route id change to 'category-mapping' | Align SPA routing with new menu id for Category Mapping. | Refactor | P3 | Navigating to Category Mapping uses 'category-mapping' path; no broken links. | Click sidebar item; verify route path and page render. | Shipped | 2025-09-14 | Update any hardcoded links.
F-018 | Products | ProductList Page | Brand & status filters | Filter by brand and product status (active/inactive/out-of-stock). | New | P3 | Combining filters narrows results AND-wise. | Apply brand + status; verify matching set. | Shipped | 2025-09-14
F-019 | Products | ProductList Page | Sort controls | Sort by newest/oldest/name asc/desc/price high/low/stock high/low. | New | P3 | Selected sort order is applied correctly and maintained with filters. | Try each sort option; verify top rows. | Shipped | 2025-09-14
F-020 | Products | ProductList Page | Pagination (page size 15) | Client-side pagination with page size 15 and numbered controls. | New | P3 | Page counts reflect total; navigating pages updates list. | Check totals; move to last page; confirm counts. | Shipped | 2025-09-14
F-022 | Products | ProductList Page | Inline variants expansion | Show product variants inline beneath a row including stock, barcode, price. | Enhancement | P3 | Products with variants show expandable area; values are correct. | Expand a row with variants; verify fields. | Shipped | 2025-09-14
F-023 | Products | ProductList Page | Export filtered results | Export current filtered/sorted products to XLSX/CSV. | New | P3 | Download reflects current view filters and sort; headers correct. | Apply filters; export; open file and verify. | Shipped | 2025-09-14
F-024 | Products | ProductList Page | Empty state & reset | Show friendly empty state when no results; provide 'Reset filters' button. | Enhancement | P3 | No-result searches show empty state; reset restores defaults. | Enter non-existing term; click reset; verify list restored. | Shipped | 2025-09-14
F-025 | Products | ProductList Page | Image fallback & accessibility | Product thumbnails include alt text and error fallback image. | Enhancement | P3 | Broken image src shows fallback; alt text present in DOM. | Tamper image url; observe fallback; inspect alt. | Shipped | 2025-09-14
F-026 | Products | ProductDetail Page | Detail header actions | Provide 'Back to list', 'Settings' modal, 'Edit description' modal. | New | P3 | Buttons render and open respective modals; close returns to view. | Click each button; verify modal open/close. | Shipped | 2025-09-14
F-028 | Products | ProductDetail Page | Variants table | Render variants with code, barcode, price, stock, status. | New | P3 | Table shows all variants and fields; empty variants handled gracefully. | Open product with variants; verify fields. | Shipped | 2025-09-14
F-029 | Products | ProductDetail Page | Not-found UX | If product ID not found, show friendly message with 'Back to list' button. | Enhancement | P3 | Invalid URL id renders not-found card; back button navigates to list. | Enter bogus id; verify UX. | Shipped | 2025-09-14
F-030 | Products | ProductDetail Page | Image fallback & alt | Main image has alt and fallback on error. | Enhancement | P3 | Broken src shows fallback; alt is set from product name. | Force error; observe fallback image. | Shipped | 2025-09-14
F-033 | Orders | OrderList Page | Table columns & actions | Show order id/date/customer/total/payment status/shipping status/order status/actions. | New | P3 | Columns render consistently; clicking id opens detail. | Scan table; click id; verify navigation. | Shipped | 2025-09-14
F-035 | Orders | OrderList Page | Internal memo CRUD | Add/edit/delete internal memos per order. | New | P3 | Memo list updates instantly; edits persist in session/mock store. | Add memo; edit; delete; verify UI state. | Shipped | 2025-09-14
F-036 | Orders | OrderDetail Page | Order summary header | Show order number, date, total, payment method, order status, shipping status. | New | P3 | Values match mock data; labels localized. | Open detail; verify header values. | Shipped | 2025-09-14
F-037 | Orders | OrderDetail Page | Items list with tax/discount | Show items with product, options, qty, price, tax, discounts. | New | P3 | Line values sum to totals; formatting correct. | Check sums against totals; verify formatting. | Shipped | 2025-09-14
F-038 | Orders | OrderDetail Page | Shipment process (simulate) | Enter carrier and tracking to mark as shipped (UI simulation). | New | P3 | After entering values and confirming, status becomes '발송 완료'. | Enter tracking; click confirm; verify status change. | Shipped | 2025-09-14 | Server integration TBD.
F-040 | Orders | OrderDetail Page | Internal memo in detail | Add/edit/delete internal memos in detail view. | New | P3 | Memo operations reflect immediately in UI. | CRUD a memo; verify changes. | Shipped | 2025-09-14
F-041 | Malls | Malls Page | Mall tiles list | List malls with platform, connection status, last sync time, sync status. | New | P3 | Tiles render with correct badges; time formats are readable. | Open page; verify badges and timestamps. | Shipped | 2025-09-14
F-042 | Malls | Malls Page | Connect new mall form | Add a new mall via API credential form (demo). | New | P3 | Submitting creates a mall entry in list with '연결 안됨' or mock connected state. | Fill form; submit; check list includes new mall. | Shipped | 2025-09-14 | Persistence TBD.
F-055 | Shared / Routing | Sidebar ID update | Set category mapping menu id to 'category-mapping' | Ensure nav uses updated route id. | Refactor | P3 | Menu link navigates correctly; breadcrumbs updated (if any). | Click from sidebar; verify correct page. | Shipped | 2025-09-14 | Audit for broken deep links.
F-031 | Products | ProductDetail Page | Description edit modal (demo) | Edit product description in modal (demo only; no persistence). | New | P4 | Typing updates local state; closing without save dismisses; save is a no-op in demo. | Open modal; type; close; reopen; content reset per design. | Shipped | 2025-09-14 | Persistence TBD with backend.
F-039 | Orders | OrderDetail Page | Refund/Cancel placeholder | Show refund button (no backend yet). | Placeholder | P4 | Button disabled or shows '미구현' toast. | Click button; verify placeholder behavior. | Shipped | 2025-09-14
F-043 | Malls | Mall Detail | Mall settings edit | Edit default shipping method, currency, and mall-specific options. | New | P4 | Editing values updates UI and mock store. | Open a mall; edit fields; verify state change. | Shipped | 2025-09-14
F-044 | Malls | Malls Page | Sync logs (demo) | View recent sync events and failure reasons in a log panel. | New | P4 | Events render with type and timestamp; errors highlighted. | Open logs; verify entries. | Shipped | 2025-09-14 | Mock data only.
F-045 | Integrations | Integrations Page | Integrations list | List external integrations with type and connection status. | New | P4 | Each integration shows name, type, status. | Open page; verify list contents. | Shipped | 2025-09-14
F-046 | Integrations | Integration Detail | Credentials & webhooks config | Edit client id/secret, callback URL, and webhook settings (demo). | New | P4 | Values editable; simple validation; saved to local/mock store. | Edit fields; hit save; verify persisted in session. | Shipped | 2025-09-14 | Do not store secrets in plain text in production.
F-047 | Integrations | Integrations Page | Webhook test event (demo) | Send a test event to verify handling (UI only). | New | P4 | Trigger shows success/failure toast and a log row. | Click 'Webhook test'; verify UI response. | Shipped | 2025-09-14 | No external calls in demo.
F-048 | Reports | Reports Page | Filters | Filter by date range, mall, product/category. | New | P4 | Changing filters updates charts and table. | Adjust each filter; observe chart/table refresh. | Shipped | 2025-09-14
F-049 | Reports | Reports Page | Charts & tables | Show sales trend, order count, top products + raw data table. | New | P4 | Charts render with consistent axes; table matches chart aggregates. | Scan charts; compare with table; verify coherence. | Shipped | 2025-09-14 | Export of raw data supported.
F-050 | Reports | Reports Page | Export data | Export current table/chart data to CSV/XLSX. | New | P4 | Download contains selected period and filters applied. | Set filters; export; verify contents. | Shipped | 2025-09-14
F-051 | Settings | Settings Page | General settings | Edit base currency and tax policy (demo). | New | P4 | Saving updates UI; values retained in session. | Change currency/tax; save; refresh (if supported). | Shipped | 2025-09-14
F-052 | Settings | Settings Page | Notifications settings (placeholder) | Toggle email/slack notifications (demo only). | Placeholder | P4 | Toggles change state; non-functional warning displayed. | Toggle on/off; verify hint message. | Shipped | 2025-09-14
F-053 | Settings | Settings Page | User accounts & roles (placeholder) | List users and set roles (admin/editor/read-only) — placeholder. | Placeholder | P4 | UI renders; editing shows '미구현' or demo behavior. | Try edit; verify placeholder behavior. | Shipped | 2025-09-14
F-054 | Shared / Style | Cards & Layout | Remove central divider & adjust padding/shadow | Visual polish: remove mid-line; unify paddings and shadows across cards. | Enhancement | P4 | No mid-divider; consistent spacing; visual regression minimal. | Compare before/after; scan across pages. | Shipped | 2025-09-14

## Types
Type
New
Enhancement
Refactor
Placeholder
Policy

## Priorities
Priority
P1
P2
P3
P4

## Statuses
Status
Shipped
Planned
In Progress
Blocked

## Sections
Sections
Products
Orders
Category Mapping
Product Classifications
Reports
Settings
Malls
Integrations
Shared / Style
Accessibility
Security